## P.I.R.A.N.H.A Backlog
PIRANHA (Phishing Identifier and Remote Access Network Hacking APIs)
TASK | POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Problem Analysis | 6
Identifying the problem |  | Mary Apelo, Dominic Ronquillo
Determining the background of the problem |  | Arnett Abarquez, Joshua Gonzales
Gathering data for reference |  | Regina Alde, Ron Garcia
Selecting the most optimal reference for the project |  | Omar Julkipli
Project Requirements | 3
GUI Design |  | Arnett Abarquez, Joshua Gonzales
Database Design |  | Regina Alde, Joshua Gonzales
Function Design |  | Mary Apelo, Dominic Ronquillo
Software Design |  | Ron Garcia, Omar Julkipli
Project Development | 5
Development of the GUI |  | Regina Alde, Joshua Gonzales
Development of the database |  | Regina Alde, Mary Apelo
Development of the function |  | Arnett Abarquez, Dominic Ronquillo
Development of the software |  | Ron Garcia, Omar Julkipli
Project Implementation/Testing | 7
Software failure testing |  | Mary Apelo, Ron Garcia
Function fault testing |  | Joshua Gonzales, Dominic Ronquillo
Error handling testing |  | Arnett Abarquez, Regina Alde
Structural testing |  | Ron Garcia, Omar Julkipli
Maintenance | 4
Testing |  | All members
Checking for software revision |  | Regina Alde, Mary Apelo, Joshua Gonzales
Revision of the software |  | Ron Garcia, Dominic Ronquillo, Omar Julkipli
Final Testing |  | All members
TOTAL | 25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0